## Roadmap
BARGAIN HUNTER
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 03/12/2024 | SPRINT2 - 04/09/2024 | SPRINT3 - 05/07/2024
| 01.01 Secure User Authentication | 4 | x
01. Subscription Management | 01.02 Plan and Price Management | 4 | x
| 01.03 Access Dedicated Customer Support | 4 | x
| 01.04 View and Apply Discounts | 4 | x
02. Sales Management | 02.01 Analyze Data with Analytics and Reporting | 4 |  | x
| 02.02 Receive Deals Alerts & Notifications | 4 |  | x
| 02.03 Integrate and Implement Marketing Strategies | 4 |  | x
03. Financial Transaction Management | 03.01 View Transaction History | 4 |  | x
| 03.02 Manage Payment Methods | 4 |  |  | x
| 03.03 Process Returns and Refunds | 4 |  |  | x
| 03.04 Ensure Security & Fraud Prevention Measures | 4 |  |  | x
04. Advertising Management | 04.01 Post Additional Ads for Premium Users | 4 |  |  | x
| 04.02 Review and Rate Posted Ads | 3
| 04.03 Manage Ad Postings | 3
| 04.04 Generate Prices for Ads | 2
05. Customer Support | 05.01 Engage with Chat Support | 4
| 05.02 Provide User Feedback | 3
| 05.03 Manage Support Tickets Efficiently | 2
|  | VELOCITY: | 16 | 16 | 16